## Sheet1
ID | Active | Task Mode | Name | Duration | Start | Finish
1 | Yes | Manually Scheduled | Plano de projeto | 6 days | 05 March 2017 17:00 | 12 March 2017 17:00
2 | Yes | Manually Scheduled | Análise de Requisitos | 7 days | 12 March 2017 08:00 | 19 March 2017 17:00
3 | Yes | Manually Scheduled | Projeto conceptual e lógico | 12 days | 19 March 2017 08:00 | 02 April 2017 17:00
4 | Yes | Manually Scheduled | Projeto físico | 42 days | 02 April 2017 08:00 | 28 May 2017 17:00
5 | Yes | Manually Scheduled | Apresentação | 4 days | 30 May 2017 08:00 | 02 June 2017 17:00